## Invoice
STATE OF HAWAII
DEPARTMENT OF LAND AND NATURAL RESOURCES
ENGINEERING DIVISION
[7 empty] | Payment No. |  | 8
PROGRESS INVOICE
FOR THE WORK PERFORMED FROM |  |  | 2023-04-01 |  | TO | 2023-04-30
[8 empty] | Date | 2023-05-01
CONTRACTOR | ABC Consultants | [5 empty] | CONTRACT NO. |  | 60000
ADDRESS | 1111 King Street | [5 empty] | JOB NO. |  | F50XX713C
| Honolulu, Hawaii 96826 | [5 empty] | PO/FINAL/No Retainage |  |  | No
PROJECT TITLE | Project ABC
CONTRACT |  |  |  |  | WORK ACCOMPLISHED
Original Contract Amount |  |  |  | 50497 | Completed to Date |  | 87.88% | $ | 58695.31
SUPPLEMENTAL CONTRACTS & CHANGE ORDERS |  |  |  |  | Retained |  | 4.394% | $ | 2934.7655 |  | 3339.65
[5 empty] | (5% max up to 50% of Contract Amount) | [5 empty] | 5%
Total Additions | 16296
Amount Subject to Payment
Total Deductions | 0 | [6 empty] | $ | 55760.54
Previous Payments to Date
Adjusted Contract Amount |  |  |  | 16296 |  |  |  | $ | 57006.36
[5 empty] | Payment Now Due |  |  | $ | -1245.82
Contract Amount as Amended |  |  |  | 66793
Remarks: | none
none
none
I certify that the above bill is correct and just and that payment thereof has not been received.
ABC Consultants
Name of Contractor
Signed By:
John Doe, President
For DLNR use only: | [5 empty] | (Typed Name and Title)
GOODS/SERVICES REC'D IN SATISFACTORY CONDITION |  |  |  |  | For DLNR use only:
Signature |  |  | Date: |  | This is to certify that this is an electronically transmitted invoice that has not been previously paid and will not be presented for payment again.
|  | Initial | Date
Invoice Rec'd |  |  |  |  | Approved:
OK to Pay | [7 empty] | /
Circle PARTIAL FINAL |  |  |  |  | Signature |  |  |  | Date
Note on M21: DLNR: 5% of 50% of Contract Amount
Note on M22: Percentage to retain if allowed by Contract
Note on J27: Amount Subject to Payment from previous invoice
Note on A48: DLNR: PM/DM to sign & date after review
Note on F51: DLNR: DLNR PM/DM to approve & sign

## Recap Sheet
|  | FOR THE PERIOD OF: |  | 2023-04-01
DEPARTMENT OF LAND AND NATURAL RESOURCES |  | TO |  | 2023-04-30
| RECAP SHEET | TO ACCOMPANY PAYMENT NO.:
8
Project: | Project ABC
ITEM | DESCRIPTION | CONTRACT AMOUNT | COMPLETED TO DATE
|  |  | % | AMOUNT
1 | Site Investigation and Research | 2154 | 100% | 2154
2 | Concept Phase | 5663 | 100% | 5663
3 | Contract Documents | 27115 | 100% | 27115
4 | Construction Administration | 4265 | 10% | 426.51
5 | Topographic Survey ATA | 4000 | 100% | 4000
6 | Reimbursables and Expenses | 2300 | 100% | 2300
7 | Additional Design Service for shelter structures | 21296 | 80% | 17036.8
8 |  |  |  | 0
9 |  |  |  | 0
10 |  |  |  | 0
11 |  |  |  | 0
12 |  |  |  | 0
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0
16 |  |  |  | 0
17 |  |  |  | 0
18 |  |  |  | 0
19 |  |  |  | 0
20 |  |  |  | 0 | 0
21 |  |  |  | 0
22 |  |  |  | 0
23 |  |  |  | 0 | 0
24 |  |  |  | 0
25 |  |  |  | 0
26 |  |  |  | 0
27 |  |  |  | 0
28 |  |  |  | 0
29 |  |  |  | 0
30 |  |  |  | 0
| TOTALS | 66793 | 87.88% | 58695.31
Note on G28: DLNR: sum of supplements, additional changes, etc. will carry over to invoice
Note on G31: DLNR: sum of supplements, additional changes, etc. will carry over to invoice

## Instructions
Procedure for Preparing Progress Invoices for DLNR Engineering Division
1. The forms are rather self-explanatory. Complete all items in red. Check red notch at corner of cells for helpful hints.
2. The order of the sheets should be:
Invoice
Recap Sheet
Contractor's back-up (as requested by PM)
3. The Recap Sheet shall have the same entries as the Compensation and Payment Schedule (S2) of the executed contract or breakdown of Purchase Orders for the project.
4. A total of 30 line items can be listed on the Recap Sheet. If additional lines are needed, an additional worksheet may be attached.
5. For each progress invoice, email a signed Invoice and Recap Sheet in PDF format to the State DLNR Project Manager. Digital signature is acceptable.
Purchase Orders(PO) or Contracts with no retainage
Be sure to select "Yes" on pulldown menu on Invoice sheet.
Final Payments:
The process is the same as monthly progress payments except the payment number shall be followed by "(FINAL)", for example "5(FINAL)" for the fifth and final payment.
Be sure to select "Yes" on pulldown menu on Invoice sheet.
Instructions for filling-out the invoice with supplemental contracts and/or change orders
1. Each supplemental and change order amount shall be totaled separately outside the "printed area" on the recap sheet.
2. Total additions shall carry over to the invoice worksheet in a different cell than the total deductions. Deductions on the Recap Sheet need to be entered as negative amounts. Please check the comments.